SECURE MESSAGING & SIGNED DOCUMENT SYSTEM

Aditya Naredla (Security Lead) · Uma Viraja (PM) · Susmitha Edara (Dev) · Sathwik Boguda (Test) · Kamal Kuturu (Integration)

# 1. Problem Statement

Modern messaging systems transmit sensitive data across networks that are insecure by default. Without cryptographic protections, every message is vulnerable to eavesdropping, MITM attacks, tampering, replay, and impersonation. Traditional systems rarely provide all four security properties simultaneously: confidentiality, integrity, authentication, and non-repudiation. Partial solutions leave exploitable gaps.

Stakeholders: End users needing private communication; organizations requiring regulatory compliance (HIPAA, GDPR) and audit trails; system administrators managing key infrastructure; course evaluators assessing applied cryptography implementation.

Why cryptography is required: Network-layer protections (firewalls, VPNs) protect the pipe, not the content. End-to-end cryptography ensures only communicating endpoints access plaintext. Digital signatures provide unforgeable sender accountability. Document hashing enables tamper-evident verification. These are minimum requirements, not optional enhancements.

# 2. Proposed Solution

A Secure Messaging and Signed Document System built on six primitives: X25519 (key exchange), HKDF-SHA256 (key derivation), AES-256-GCM (authenticated encryption), Ed25519 (digital signatures), SHA-256 (document hashing), and a local blockchain for key registration. Implements a TLS-inspired handshake, encrypted messaging with replay protection, and document signing with detached signatures.

# 3. MVP Definition & Success Criteria

| # | Success Criterion | Measurement |
| --- | --- | --- |
| SC1 | Signed key exchange completes; shared session key derived | Both sides output identical session key hash |
| SC2 | Messages encrypted E2E; no plaintext on the wire | Wireshark capture shows only ciphertext |
| SC3 | Tampered ciphertext detected and rejected | Byte-flip triggers ERR_TAG_INVALID; msg dropped |
| SC4 | Replayed messages detected and rejected | Resent packet triggers ERR_SEQ_REPLAY; msg dropped |
| SC5 | MITM key substitution detected | Rogue key triggers ERR_SIG_INVALID; handshake aborts |
| SC6 | Documents signed and independently verified | Receiver recalculates SHA-256; verifies Ed25519 sig offline |
| SC7 | Public keys registered on blockchain and retrievable | Key lookup matches on-chain registration |

Demo story: Alice and Bob handshake → exchange encrypted messages. Eve attacks live: MITM key injection (rejected), ciphertext byte-flip (rejected), replay (rejected). Alice signs a document; Bob verifies offline. Blockchain confirms key ownership.

# 4. Non-Goals & Scope Boundaries

| Non-Goal | Why Out of Scope |
| --- | --- |
| GUI / web interface | Crypto is the deliverable, not UI. CLI demonstrates all security properties. |
| Multi-party group chat | Group key agreement (MLS) is graduate-level. 1-to-1 covers all required primitives. |
| Denial-of-service defense | DoS is a networking problem. We add handshake timeout but don't optimize for adversarial load. |
| Side-channel attack defense | Requires hardware instrumentation. We rely on Curve25519's constant-time design. |
| Distributed blockchain | Consensus (Raft, PBFT) is out of scope. Single-node proves immutable-ledger concept. |
| Persistent message history | Real-time messaging only. Searchable encryption is a separate research topic. |
| Within-session forward secrecy | Per-session forward secrecy via ephemeral X25519. Double Ratchet is a stretch goal. |

# 5. Top-5 Risk Register

| # | Risk | L | I | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | AES-GCM nonce reuse (leaks auth key) | Low | Crit | Nonce = base_nonce XOR monotonic seq. No manual nonce API. Hard rekey at 2^32. Unit test verifies uniqueness over 10k msgs. |
| R2 | Module integration failures | High | High | Interface spec frozen at w5. Weekly integration smoke tests from Week 4. JSON schema validation on all message types. |
| R3 | Key mgmt bugs (plaintext keys, not zeroed) | Med | Crit | SecureSessionKey prevents serialization. PR checklist: "key zeroed after use". Automated grep for raw key bytes in test output. |
| R4 | Team member unavailable in critical sprint | Med | Med | Every module has backup owner. Pair programming on P0 issues. Shared repo with CI means any member can pick up. |
| R5 | Blockchain component delays MVP | Med | Low | Blockchain scoped post-MVP (Sprint 6). SC1–SC6 don't depend on it. SC7 can demo standalone. |

# 6. GitHub Board (≥12 Issues)

18 issues prioritized across MVP, Docs, Tests, and Demo. Board on GitHub Projects, 1-week sprints.

| # | Issue | Owner | Pri | Cat | Sprint | Wk | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Protocol spec + message format | Aditya | P0 | Docs | S1 | 1 | Backlog |
| 2 | Threat model + risk register | Aditya | P0 | Docs | S1 | 1 | Backlog |
| 3 | Repo, CI, linting, .gitignore | Susmitha | P1 | MVP | S1 | 1 | Backlog |
| 4 | X25519 key generation | Aditya | P0 | MVP | S2 | 2 | Backlog |
| 5 | Ed25519 signing key gen | Uma | P0 | MVP | S2 | 2 | Backlog |
| 6 | TLS handshake protocol | Aditya | P0 | MVP | S3 | 3 | Backlog |
| 7 | HKDF session key derivation | Aditya | P0 | MVP | S3 | 3 | Backlog |
| 8 | AES-256-GCM pipeline | Susmitha | P0 | MVP | S4 | 4 | Backlog |
| 9 | Message framing (ver/type/seq) | Sathwik | P1 | MVP | S4 | 4 | Backlog |
| 10 | Seq tracking + replay reject | Susmitha | P0 | MVP | S5 | 5 | Backlog |
| 11 | Ed25519 sign-then-encrypt | Uma | P0 | MVP | S5 | 5 | Backlog |
| 12 | TCP + heartbeat + close | Sathwik | P1 | MVP | S5 | 5 | Backlog |
| 13 | Blockchain key registry | Aditya | P1 | MVP | S6 | 6 | Backlog |
| 14 | Doc hashing + file signing | Kamal | P0 | MVP | S7 | 7 | Backlog |
| 15 | Blockchain audit trail | Kamal | P1 | MVP | S7 | 7 | Backlog |
| 16 | MITM + tamper simulation | Sathwik | P0 | Tests | S8 | 8 | Backlog |
| 17 | Replay + forgery simulation | Sathwik | P0 | Tests | S8 | 8 | Backlog |
| 18 | Demo + benchmarks + report | Kamal | P1 | Demo | S9 | 9 | Backlog |